## Sheet1
BUG REPORT
Bug ID | Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
BUG-001 | No validation on First Name field | 1. Go to Signup page.2. Enter 12 as First Name.3. Click Sign Up. | Should only accept alphabets. | Accepts numeric input like 12. | Medium | High | Not Fixed
BUG-002 | No validation on Last Name field | 1. Go to Signup page.2. Enter 12 as Last Name.3. Click Sign Up. | Should only accept alphabets. | Accepts numeric input like 12. | Medium | High | Not Fixed
BUG-003 | Invalid email format accepted | 1. Go to Signup page.2. Enter 12 as Email.3. Click Sign Up. | Should validate proper email format (e.g., example@gmail.com). | Accepts invalid email like 12. | high | High | Not Fixed
BUG-004 | Weak password accepted | 1. Go to Signup page.2. Set password as 00.3. Click Sign Up. | Password should require at least 8 chars with mix of letters, numbers, and symbols. | Accepts weak 2-digit password. | high | High | Not Fixed
BUG-005 | Google/Apple sign-in not functional | 1. On Signup page, click “Continue with Google” or “Continue with Apple”. | Should redirect to respective authentication page. | Nothing happens — login not triggered. | high | High | Not Fixed
BUG-006 | Profile overview missing | 1. Log in successfully.2. Go to Profile → Overview. | Profile info should display in Overview. | Profile section missing in Overview, though it shows on top of dashboard. | Medium | High | Not Fixed
BUG-007 | Submit button not working on Profile Details | 1. Go to Profile → Details.2. Edit any details and click Submit. | The updated information should save, and a success pop-up or alert should appear. | Submit button not working — no action or confirmation after clicking. | Medium | Medium | Not Fixed
BUG-008 | Location not showing in profile overview | 1. Go to Profile → Details.2. Add location and save.3. Check Overview. | Added location should display in Overview. | Overview shows N/A for location. | Low | Medium | Not Fixed
BUG-009 | Incorrect placeholder in Event Duration field | 1. Go to Dashboard → Add New Campaign.2. Check the Event Duration input field. | Placeholder should display “Start Date” and “End Date.” | Placeholder text is incorrect or missing. | Low | Medium | Not Fixed
BUG-010 | Start Date field not working in Add Campaign | 1. Go to Dashboard → Add New Campaign.2. Try selecting a Start Date in Event Duration. | Start Date calendar picker should open and allow date selection. | Start Date field is not functional (no date can be selected). | high | High | Not Fixed
BUG-011 | Role field in Add Stakeholder not dropdown | 1. Go to Add Stakeholder section.2. Check the Role input field. | Role field should be a dropdown to select predefined roles. | Role field is a text input, not a dropdown. | Medium | Medium | Not Fixed
BUG-012 | Add Stakeholder button not working | 1. Go to Add Stakeholder section.2. Fill in details and click Add Stakeholder. | New stakeholder should be added and appear in the list. | Add Stakeholder button not responding or performing any action. | high | High | Not Fixed
BUG-013 | Previous task info retained after cancel | 1. Go to Dashboard → Create New Campaign.2. Click Add New Task, fill in task details, then click Cancel.3. Again, click Add New Task. | The task form should reset and appear blank when reopened. | The previously entered task information is still displayed in the form. | Medium | High | Not Fixed
BUG-014 | Progress status value not updating | 1. Go to Dashboard → Create New Campaign.2. Add a new task.3. Select any Progress Status value. | Selected status should display correctly (e.g., “In Progress” or “Completed”). | Progress status always shows false regardless of selected option. | Medium | High | Not Fixed
BUG-015 | Milestone creation automatically creates a task | 1. Go to Dashboard → Create New Campaign.2. Add a new Milestone only. | Only milestone should be created. | When milestone is added, a task is also created automatically. | Medium | High | Not Fixed
BUG-016 | Delete milestone confirmation button not working | 1. Go to Dashboard → Create New Campaign.2. Try deleting a milestone.3. Observe the confirmation popup. | “Delete” button should remove the milestone after confirmation. | Popup appears (“Are you sure to delete?”) but Delete button doesn’t work. | high | High | Not Fixed
BUG-017 | Blank page appears after creating new campaign | 1. Go to Dashboard → Create New Campaign.2. Fill in all required info.3. Click Add New Campaign. | System should save campaign and navigate back or show success message. | Clicking Add New Campaign leads to a blank page. | high | High | Not Fixed
BUG-018 | Default rating showing 4.5 in Vendor Management | 1. Go to Vendor Management page. | Ratings should be based on vendor data or blank if no vendors. | Shows default rating 4.5 even without vendors. | Low | Low | Not Fixed
BUG-019 | “No vendor found” message not centered | 1. Go to Vendor Management with no vendors added. | “No vendor found” message should appear centered on screen. | Message appears misaligned (not centered). | Low | Low | Not Fixed
BUG-020 | Vendor creation accepts invalid data | 1. Go to Vendor Management → Add New Vendor.2. Leave fields blank or enter invalid data (e.g., Name 1234, Email 12).3. Click Save. | Validation errors should appear; invalid data not saved. | Accepts invalid input and saves vendor, which doesn’t appear in list. | high | High | Not Fixed
BUG-021 | Vendor profile description shows as “N/A” | 1. Go to Vendor Management.2. Add a new vendor and save.3. Click on vendor profile. | Description should display properly under vendor name. | Shows N/A instead of description. | Medium | Medium | Not Fixed
BUG-022 | Validation pop-up appears behind “Add New Vendor” page | 1. Go to Vendor Management page.2. Click Add New Vendor.3. Leave all fields empty and click Save. | Validation pop-up or alert should appear clearly on top of the page. | Pop-up appears behind the “Add New Vendor” page and is not visible to the user. | Medium | High | Not Fixed
BUG-023 | “No contract found” text not centered | 1. Go to Contact page.2. Ensure no contracts are available. | “No contract found” message should be displayed centered on the page. | Message appears misaligned and not centered. | Low | Low | Not Fixed
BUG-024 | 404 error displayed after page refresh | 1. Log in and navigate to any internal page (e.g., Dashboard, Vendor Management, etc.).2. Refresh the browser page. | The same page should reload properly without errors. | After refreshing, the page shows a 404 Not Found error. | high | High | Not Fixed