## Sheet1
BUG REPORT
Bug ID | Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
Bug_001 | Missing button text in Basic Plan | 1. Log in to school side2. Navigate to plans page3. Check Basic Plan section | Basic Plan button should display label text (e.g., "Basic Plan") | Basic Plan button text is missing | medium | Medium | Not Fixed
Bug_002 | Duplicate text in Basic Plan | 1. Log in to school side2. Navigate to plans page3. Check Basic Plan section | Basic Plan should display text once, clearly and correctly | Basic Plan shows the same text written twice | medium | Medium | Not Fixed
Bug_003 | Choose Plan button not working | 1. Log in to school side2. Navigate to plans page3. Click on “Choose Plan” button in plan section | Clicking “Choose Plan” should trigger proceed to payment (same as clicking div) | “Choose Plan” button does nothing when clicked | high | High | Not Fixed
Bug_004 | Dashboard not redirecting after payment | 1. Log in to school side2. Select a plan3. Enter valid payment information4. Submit payment | After successful payment, user should be redirected to dashboard | User stays on the same page, no redirect to dashboard | high | High | Not Fixed