## Sheet1
BUG REPORT
Bug ID | Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
Bug_001 | Dashboard navbar not scrollable, Logout button not at end | 1. Log in to the application. 2. Open Dashboard. 3. Observe navbar. | Navbar should be scrollable; Logout button fixed at the end. | Navbar is not scrollable; Logout button misplaced. | Medium | High | Not Fixed
Bug_002 | Field trip link icon incorrect in dashboard | 1. Go to Dashboard. 2. Locate Field Trip link. | Correct icon should display. | Incorrect icon displayed. | Low | Medium | Not Fixed
Bug_003 | Average rating drive icon color incorrect | 1. Go to Dashboard. 2. View Average Rating for driver. | Icon color should match design standards. | Icon color is incorrect. | Low | Low | Not Fixed
Bug_004 | Missing icons in Upcoming Trips section | 1. Open Dashboard. 2. Go to Upcoming Trips. 3. Check Student and Driver entries. | Icons for Student and Driver should be visible. | Icons missing. | Medium | Medium | Not Fixed
Bug_005 | View proposal icon incorrect | 1. Go to relevant section with proposals. 2. Locate View Proposal icon. | Correct icon should be used. | Incorrect icon displayed. | Low | Medium | Not Fixed
Bug_006 | Recent notifications missing time | 1. Go to Dashboard. 2. Open Recent Notifications list. | Each notification should display its timestamp. | Notification time is missing. | Medium | Medium | Not Fixed
Bug_007 | "View All" color mismatch in dashboard | 1. Go to Dashboard. 2. Locate "View All" link/button. | Color should be blue as per design. | Color is red. | Low | Medium | Not Fixed
Bug_008 | Profile border missing in dashboard | 1. Go to Dashboard. 2. Check profile section. | Profile should have border as per design. | Border is missing. | Low | Medium | Not Fixed
Bug_009 | Field trip link icon mismatch in Post New Trip | 1. Go to "Post New Trip" section. 2. Locate Field Trip link. | Icon should match design specifications. | Icon does not match design. | Low | Medium | Not Fixed
Bug_010 | Placeholder text has inconsistent colors | 1. Open the page"Post New Trip" containing the placeholder field. 2. Observe the placeholder text. | Placeholder text should have a single, consistent color. | Placeholder text appears half in black and half in gray. | Low | Medium | Not Fixed
Bug_011 | "One-time" and "Recurring" buttons have inconsistent styles | 1.Open post new trip Navigate to the section with "One-time" and "Recurring" buttons. 2. Compare button styles. | Both buttons should follow the same style guide. | Button styles differ in appearance. | Low | Medium | Not Fixed
Bug_012 | Preferred driver gender field not in design but present in website | 1. Go to "Post Trip" page.2. Check for "Preferred Driver Gender" field. | Field should not exist as it’s not in the approved design. | Field is present on the website. | Low | Medium | Not Fixed
Bug_013 | Extra top margin in Location and Requirement sections | 1. Go to "Post Trip" page. 2. Compare the top spacing of Location and Requirement sections with design. | Top margin should match design spacing. | Top margin is larger than in design. | Low | Low | Not Fixed
Bug_014 | Post Trip button background color mismatch | 1. Go to "Post Trip" page. 2. Observe the "Post Trip" button color. | Background should be blue as per design. | Background is red. | Low | Medium | Not Fixed
Bug_015 | Active trip background and border color mismatch | 1. Go to "Live Tracking" page. 2. Check active trips section. | Div background and border color should match design. | Background and border color are different from design. | Low | Medium | Not Fixed
Bug_016 | Status icon dot missing status text | 1. Go to "Live Tracking" page. 2. View status section for trips. | Dot icon should be shown with status text. | Dot icon should be shown with status text.Dot icon should be shown with status text. | Medium | Medium | Not Fixed
Bug_017 | ETA background and text color mismatch | 1. Go to "Live Tracking" page. 2. Check ETA display (e.g., "ETA: 15 min"). | ETA background and text color should match design (black text). | ETA has a background and text color differs from design. | Low | Medium | Not Fixed
Bug_018 | Interactive map design change in Live Tracking | 1. Go to "Live Tracking" page.2. Observe interactive map. | Map should match approved design. | Map design is different. | Medium | Medium | Not Fixed
Bug_019 | GPS icon replaced with bus icon in number of buses section | 1. Go to "Live Tracking" page.2. Check number of buses display. | GPS icon should be shown as per design. | Bus icon is displayed instead. | Low | Medium | Not Fixed
Bug_020 | Navbar icons mismatch with design | 1. Navigate through navbar. | Icons should match approved design. | All icons are different from design. | Medium | High | Not Fixed
Bug_021 | Trip Management - Post Trip button background color mismatch | 1. Go to "Trip Management".2. Locate Post Trip button. | Background should match design. | Background color is different. | Low | Medium | Not Fixed
Bug_022 | Trip Management - Active icon mismatch | 1. Go to "Trip Management".2. Check active icon. | Icon should match design. | Icon is different from design. | Low | Medium | Not Fixed
Bug_023 | Recurring, One-time, and Active colors mismatch | 1. Go to "Trip Management". 2. View recurring, one-time, and active trip labels. | Text and background colors should match design. | Colors are different. | Low | Medium | Not Fixed
Bug_024 | Trip Management - Active field trip link icon mismatch | 1. Go to "Trip Management". 2. Check active field trip link. | Icon should match design. | Icon is different. | Low | Medium | Not Fixed
Bug_025 | Trip Management - Pending and Recurring missing | 1. Go to "Trip Management". | Pending and Recurring statuses should be displayed. | Missing from interface. | Medium | High | Not Fixed
Bug_026 | Trip Management - Pending edit/delete icon mismatch | 1. Go to "Trip Management". 2. Locate pending trip actions. | Edit and delete icons should match design. | Icons are different from design. | Low | Medium | Not Fixed
Bug_027 | Trip Management - Bus text font size too large | 1. Go to "Trip Management". 2. View bus text. | Font size should match other text elements. | Bus text font size is larger than others. | Low | Low | Not Fixed
Bug_028 | Proposal numbering position mismatch after driver request | 1. Go to Driver Request section after posting a trip. 2. Check proposal numbering position. | Numbering should appear on the right side of the title. | Numbering appears under "Driver Request" text. | Low | Medium | Not Fixed
Bug_029 | Missing details in Invite Drivers section | 1. Go to Invite Drivers section. | All driver details should be shown as per design. | Some details are missing. | Medium | Medium | Not Fixed
Bug_030 | Suspended status color/icon mismatch in Hired Driver section | 1. Go to Hired Driver → Suspended driver. 2. Click any suspended driver. | Suspended status should be red with an icon. | Status is green and has no icon. | Medium | High | Not Fixed
Bug_031 | Verify and Reject options not in design | 1. Go to Verify Driver section. | Verify and Reject should not appear (not in design). | Both options appear. | Low | Low | Not Fixed
Bug_032 | Suspended status color mismatch in Driver Verification details | 1. Go to Driver Verification → Submission Details. 2. View status. | Suspended should be red. | Status is black. | Medium | Medium | Not Fixed
Bug_033 | Verified status color mismatch in Driver Verification details | 1. Go to Driver Verification → Submission Details. 2. View status. | Verified should be green. | Status color differs from design. | Medium | Medium | Not Fixed
Bug_034 | Pending status text and color mismatch in Driver Verification details | 1. Go to Driver Verification → Submission Details. 2. View pending status. | Text should say "Pending", with yellow text and yellow background. | Text says "Reject" and status is green. | High | High | Not Fixed
Bug_035 | School info icon mismatch in Settings | 1. Go to Settings page. 2. Locate School Info section. | Icon should match design specifications. | Icon is different from design. | Low | Medium | Not Fixed