## Sheet1
BUG REPORT
Bug ID | Title | Steps to Reproduced | Expected Result | Actual Result | Severity | Priority | Status
Bug_01 | App logo does not match the intended logo (shows Flutter default logo) | 1. Install the app on the device 2. Observe the app icon/logo on the home screen and in the app launcher | The app logo should display the official logo of the application | App logo shows Flutter default logo, not the intended branded logo | Medium | Medium | Fixed
Bug_02 | "Password Recovery" Title Misaligned on Screen | 1. open app 2.Click "Forgot Password" on Login screen. 2. Observe the title on the next screen. | Title should be center aligned at top of the screen. | Title appears left-aligned instead of centered. | low | Low | Fixed
Bug_03 | UI formatting issue – Text alignment for "Forget your password" and "Continue" | 1. Open app 2. Tap Forgot Password 3. Observe text under the heading | Text should be on two separate lines with normal style (not underlined or colored) | App displays "Forget your password and continue" in a single line, not matching design | low | Medium | Fixed
Bug_04 | UI text mismatch – Resend verification code message incorrect | 1. Open app 2. Go to Forgot Password → Resend code option | Message should read: "Code resent successfully. Please check your email or spam folder for the verification code." | App displays "Resend your verification code, kindly check the email", not matching the expected text | low | Medium | Fixed
Bug_05 | UI inconsistency – Reset Password button placement different from design | 1. Open app 2. Complete OTP and reach Password Reset screen 3. Observe button position | Continue and Cancel buttons should appear directly below input fields, aligned as per design mockup | App places the Reset Password button at the very bottom of the screen, not following design | low | Medium | Not Fixed
Bug_06 | Label Missing for Title Input Field | 1. Open app 2.click Map and press '+' icon 3.Go to Add Place | Label “Title” should appear above input field | Label missing, only placeholder “Explore zoo” shown instead of Enter Title | Medium | Medium | Not Fixed
Bug_07 | "Add Place" Title Misaligned on Screen | 1. open app 2.click Map and press '+'icon 3.Go to Add Place to bucketlist | Title should be center aligned at top of the screen. | Title appears left-aligned instead of centered. | low | Low | Fixed
Bug_08 | Incorrect button text displayed as "Upload" instead of "Add Place" | 1. Open the app 2.Go to Map 3. Navigate to Add Place to Bucketlist screen | The button should display "Add Place" as per the design mockup. | Button text shows "Upload" instead of "Add Place", causing UI inconsistency. | low | Medium | Not Fixed
Bug_09 | Search icon is too large in search bar | 1. Open the app 2. Go to Map 3. Observe the search icon size | Search icon should be proportional to the input field size. | Search icon appears too large, affecting UI balance. | low | Medium | Fixed
Bug_10 | Search bar corners are not rounded | 1. Open the app 2. Navigate to the search bar interface 3. Observe the search bar design | Search bar should have rounded corners as per the original design. | Search bar corners are square-shaped, not matching the mockup. | low | Medium | Not Fixed
Bug_11 | Incorrect search icon and color used | 1. Open the app 2. Go to Map 3. Compare icon color and design with the original mockup | Icon should match the style and color defined in the design system. | A different icon and color variation are used instead of the original design. | Medium | Medium | Not Fixed
Bug_12 | Radio Button Color Does Not Change on Selection | 1. Open Add Memory screen 2. Select a radio option | Selected radio button color should change from black to purple | Color remains black after click | low | Medium | Not Fixed
Bug_13 | No Tick Icon for Selected City | 1. go to map 2.add memory 3.Select a city from dropdown | Tick/checkmark should appear next to selected city | No icon shown | low | Medium | Fixed
Bug_14 | No Tick Icon for Selected Country | 1. go to map 2.add memory 3.Select a country from dropdown | Tick/checkmark should appear next to selected country | No icon shown | low | Medium | Fixed
Bug_15 | No Tick Icon for Selected Category | 1. go to map 2.add memory 3.Select a category from dropdown | Tick/checkmark should appear next to selected category | No icon shown | low | Medium | Fixed
Bug_16 | Date Label Mismatch | 1. go to map 2.add memory 3.Observe the placeholder | Label should be "when did you visist?" | Label shown as “when to go?” | low | Low | Not Fixed
Bug_17 | "Done" Text Instead of "OK" | 1. Confirm date | Button should say "OK" | Button says "Done" | low | Low | Not Fixed
Bug_18 | Button Label Incorrect: “Add to Map” | 1. Add Memory in map 2.View bottom button | Should be: “Add Memory” | Displays: “Add to Map” | Medium | High | Not Fixed
Bug_19 | Label Mismatch: “Select Category” | 1.In add memory 2. View label above category field | Should display: “Select Category” | Label says “Category” | low | Medium | Not Fixed
Bug_20 | Mismatch in "Resend Code" Text | 1. Go to OTP verification screen. 2. Read the resend message. | Should display: “Don’t have received any code? Resend” | Displays: “Have not received code? Resend” | low | Low | Not Fixed
Bug_21 | “Map Shared” Text Missing | 1. View bottom of map | Text “Map Shared” should appear | Text not shown | low | Medium | Not Fixed
Bug_22 | Camera and Gallery Icon Color Incorrect | 1. Open app. 2. Navigate to Add Memory screen. 3. Observe the camera and gallery icons. | Icons should be black. | Icons appear in purple. | Medium | Medium | Not Fixed
Bug_23 | Gallery Icon Shape Incorrect | 1. Open app. 2. Go to Pick from Gallery option. 3. Observe the shape and design of the gallery icon. | Gallery icon should match actual design. | Gallery icon is different from expected. | low | Low | Not Fixed
Bug_24 | Upload Button Text Mismatch | 1. Open app. 2. Navigate to media upload area.3. Check text near the buttons. | Text should be “Record with camera” and “Upload media from gallery”. | Text shows “Pick from camera” and “Pick from Gallery”. | low | Medium | Not Fixed
Bug_25 | Upload Media Popup Frame Size Incorrect | 1. Navigate to Upload Media section. 2. Observe popup size. | Frame should match screenshot layout with proper padding and spacing. | Popup is smaller in app. | Medium | Medium | Not Fixed
Bug_26 | Missing Close (X) Icon on Upload Media Popup | 1. Go to Upload Media screen. 2. Look for close (X) icon. | There should be a close (X) icon in the top-right corner of popup. | Close icon is missing. | Medium | Medium | Not Fixed
Bug_27 | Incorrect Text Capitalization - Add a Note | 1. in add memory 2.Go to Add Note screen. | Text should be "Add a Note". | Text in app is "Add A Note". | low | Low | Not Fixed
Bug_28 | Country code not displayed for phone numbers | 1. Open the app 2. go to map 3.add memory 4. select country | Phone number should display with correct country code prefix (e.g., Pakistan +92, US +1). | App displays only the local phone number, missing the country code prefix. | Medium | High | Not Fixed
Bug_29 | Location Pin Icon Missing | 1. View top area of map | Location icon should appear to indicate current position | No location pin visible | High | High | Not Fixed
Bug_30 | No User Avatars Displayed on Map | 1. View map screen bottom area | Small circular user photos should appear to show shared users | No users shown | Medium | Medium | Not Fixed
Bug_31 | Incorrect Label in Country Search | 1. Open "Select Country" screen | Should say “Search your Country” | Shows “Search Countries” | low | Low | Not Fixed
Bug_32 | Some Countries Missing in List | 1. Open country dropdown | Full list of countries should be displayed | Some countries are missing | Medium | Medium | Not Fixed
Bug_33 | Country Flags Display Shape Incorrect | 1. View country list in dropdown | Flags should appear in circular shape | Flags are shown in rectangular shape | low | Medium | Not Fixed
Bug_34 | Incorrect Label in City Search Bar | 1. Open "Select City" screen | Should display “Search your City” | Shows “Search Cities” | low | Low | Not Fixed
Bug_35 | Incomplete List of Cities | 1. Open city selection dropdown | Dropdown should contain wide range of cities | Only limited cities shown | Medium | Medium | Not Fixed
Bug_36 | Missing Location in Friend’s Profile | 1. Go to Friends page. 2. Open any friend's profile. | Location info should be visible. | Location is missing. | Medium | Medium | Not Fixed
Bug_37 | Friend Profile Text Formatting Issue | 1. Open a friend's profile. | "Memories" and "Places Visited" should be bold. | Text is not bold. | low | Low | Not Fixed
Bug_38 | No option to delete added emoji | 1. Add emoji in memory/chat/comment 2. Try to remove it | User should be able to remove added emoji | No option to delete or undo emoji | medium | Medium | Not Fixed
Bug_39 | Invalid error message on signup (first/last name with number) | 1. Go to Signup screen 2. Enter number in first name 3. Enter number in last name 4. Submit | Clear error: "Name should not contain numbers" | We can make account using numbers in name field. | High | High | Not Fixed
Bug_40 | Weak passwords accepted | 1. Go to Signup screen 2. Enter weak password like 123456 or asfaasfa 3. Submit the form | App should reject weak passwords and show a message like: "Password must include uppercase, lowercase, number, and special character" | Weak passwords are accepted without any validation or warning | High | High | Not Fixed
Bug_41 | App crashes when viewing friend's shared memory | 1. Go to "Friends" page 2. Click on any friend from your friend list 3. Tap on “Shared Memory” tab | App should load and show shared memories with that friend | App crashes and redirects to the login screen | high | High | Not Fixed
Bug_42 | Memory can't be added directly from timeline | 1. Go to Timeline page 2. Tap the "+" (plus) icon to add a memory 3. Fill in details and press submit 4. OR press Share with... instead | Memory should be added successfully in both cases | Direct add shows server error: memory only adds if "Share with" is selected | High | Medium | Not Fixed
Bug_43 | Profile update allows empty Name and Address fields | 1. Go to Profile section 2. Leave Name and Address fields empty 3. Tap Update/Save | System should show validation errors:– “Name cannot be empty”– “Address cannot be empty” | Profile updates with empty fields; values disappear from profile view | Medium | High | Not Fixed
Bug_44 | Address field accepts invalid input like numbers only | 1. Go to Profile section 2. Enter numeric-only address (e.g., “12345”) 3. Tap Update/Save | System should reject number-only address and show validation error | Numeric-only address is accepted and saved without any warning | low | Medium | Not Fixed
Bug_45 | Memory action options remain stuck on screen after navigation | 1. Go to the Map page 2. Tap on any memory 3. Click on the picture 4. Tap the 3 dots (•••) menu 5. Do not select "Edit Memory" or "Delete Memory" 6. Navigate to another page | The option menu should auto-close or disappear when navigating away | The "Edit Memory" and "Delete Memory" options stay visible and stuck on screen across pages | Medium | High | Fixed
Bug_46 | Newly added place does not appear immediately in "See All" section | 1. Go to Home Page 2. Tap on See All under "Add More Places" 3. Add a new place 4. Return to the list | The newly added place (with its image) should appear instantly in the list | New place is not shown until the app is closed and reopened; then it appears correctly | Medium | Medium | Not Fixed
Bug_47 | Unable to view/select all friends when more than 5 are available (no scroll option) | 1. Open app 2. Go to Add Bucket or Add Memory section 3. Choose Share with Friends 4. If friends list is 6 or more, try to select the 6th friend or beyond | The list should be scrollable, allowing selection of all friends. | Only the first 5 friends are visible; remaining friends cannot be viewed or selected due to missing scroll option. | High | High | Not Fixed
Bug_48 | No validation between selected country and city in location selection | 1. Open app 2. Navigate to Add Memory or Add Place to Bucket List 3. Select a country (e.g., Pakistan) 4. Select a city unrelated to that country (e.g., New York) 5. Save the entry | The system should only allow cities that belong to the selected country, or show an error message for mismatched selection. | App allows any city to be selected for any country without validation, leading to incorrect location data. | Medium | High | Not Fixed
Bug_49 | Mismatch in Streak Count on Friends Page | 1. Go to Friends screen. 2. Note streak number. 3. Click friend to view details. | Streak number should match on both views. | Friends screen shows 2, detail view shows 6 days. | Medium | Medium | Not Fixed