## Sheet1
BUG REPORT
Bug ID | Title | Steps to Reproduced | Expected Result | Actual Result | Severity | Priority | Status
Bug_01 | Mismatch in Streak Count on Friends Page | 1. Go to Friends screen. 2. Note streak number. 3. Click friend to view details. | Streak number should match on both views. | Friends screen shows 2, detail view shows 6 days. | Medium | Medium | Not Fixed
Bug_02 | Address field accepts invalid numeric-only input | 1. Go to the address input field. 2. Enter only digits (e.g., "0000"). 3. Submit/update the form. | System should show a validation error for numeric-only addresses. | System accepts numeric-only address and updates successfully. | Medium | High | Not Fixed
Bug_03 | “Tap to Complete” in Bucket List opens Add Memory page | 1. Go to Bucket List. 2. Click the ellipse (three dots) on an item. 3. In the menu showing Edit, Delete, Create Memory, and Tap to Complete, select “Tap to Complete.” | Item should be marked as completed or show completion confirmation. | “Tap to Complete” option opens Add Memory page instead of completing the item. | low | High | Not Fixed
Bug_04 | Map search results persist after navigation and refresh | 1. Search any location on Map page. 2. Navigate to another page. 3. Refresh and return to Map page. | Search results should clear automatically when leaving or refreshing the page. | Previous search results still display until manually cleared. | Medium | Medium | Not Fixed
Bug_06 | “Login Required” popup appears after signing in with Google | 1. Open the app. 2. Sign in using Google. 3. Try to access a feature that requires login. | User should be taken directly to the feature after successful Google sign-in. | “Login Required” popup appears, asking the user to log in or create an account despite already being signed in. | high | High | Not Fixed
Bug_07 | Clicking Weekly Streak opens Add Memory page | 1. Go to the Weekly Streak section. 2. Click on it. | Weekly Streak details or related streak page should open. | Add Memory page opens instead of the Weekly Streak details. | Medium | High | Not Fixed
Bug_08 | Bucket List options popup sticks to page while scrolling | 1. Go to Bucket List. 2. Click the three dots on any item to open the options popup (Edit, Delete, Create Memory). 3. Scroll the page. | Options popup should close or remain positioned with the related item. | Options popup stays fixed on the page while scrolling, detached from its related item. | low | Medium | Not Fixed